# TG-05 — Pre-Wageningen Final Preparation

J. Ianelli, JMWG Chair

11 June 2026

# Pre-Wageningen Final Preparation

Date: Thursday, 11 June 2026, 15:00–16:30 CEST (90 min) Mode: Zoom / Teams (online) Chair: J. Ianelli Purpose: Close all open items before the Wageningen MSE workshop (15–19 June). No new MPs, no new metrics, no new OM axes after this call.

## 1. Agenda (90 minutes, strict time-boxes)

| Time | Item | Owner | Output |
| --- | --- | --- | --- |
| 15:00–15:05 | Opening, agenda adoption, declaration of pre-circulated materials received. | Chair | Recorded attendance, confirmation of read-aheads. |
| 15:05–15:20 | Conclude the stock-hypothesis treatment. Close from TG-04. Either confirm the agreed treatment (single-stock h1, two-stock h2, or weighted combination) or invoke the documented fallback. | Chair / WMR / Chile / Peru | Decision recorded; SCW17-Doc01 updated. |
| 15:20–15:35 | Finalise performance metrics, time horizons, and risk tolerance for Wageningen (MSE-02). Conservation metrics (P(B<BLIM), P(B<BMSY)), yield/AAV, TAC-stability; 5/10/20-yr horizons; SPRFMO risk band. | Chair | Final metric list signed off; SCW17-Doc03 updated. |
| 15:35–15:55 | Freeze MP specifications (MSE-01). Data streams used by each MP, lag/frequency, tuning targets, HCR form, Buffer/K60 settings. No new MPs may be added after this item. | WMR / Chile / Peru | MP register frozen; SCW17-Doc03 finalised. |
| 15:55–16:15 | Agree complete robustness scenario matrix (MSE-03). Reference set vs. robustness set; ENSO / offshore-drop / catchability / index-bias scenarios; pass/fail criteria for advancement to SC14. | WMR | Robustness matrix signed off; SCW17-Doc04 updated. |
| 16:15–16:25 | Cross-platform validation protocol. FLR vs. RTMB/OpenMSE: which metrics are compared, on which OM, by whom (WMR / Chile / Peru), and by when. Assign owners. | Chair / WMR | Owner-and-deadline table; SCW17-Doc05 initiated. |
| 16:25–16:30 | Wageningen logistics. Trade-off presentation format (Slick / worm plots / Kobe-style); decision-making protocol; daily report-out cadence. | Chair | Format agreed; circulate Wageningen-week agenda within 48 h. |

### Decisions to be recorded

- Stock-hypothesis treatment for advice.

- Final performance-metrics list with time horizons and risk tolerance.

- Frozen MP specifications (data, tuning, HCR, Buffer/K60).

- Complete robustness-scenario matrix with pass/fail criteria.

- Cross-platform validation owners and timeline.

- Wageningen trade-off presentation format and decision-making protocol.

### Pre-circulated reading (deadline: COB Friday 6 June)

- SCW17-Doc01 — Benchmark outcomes for MSE conditioning (Chair — draft)

- SCW17-Paper-02 — Reference Points (Chair — published 29 May)

- SCW17-Doc02 — OM conditioning and diagnostics (WMR — full draft)

- SCW17-Doc03 — Candidate MPs and performance metrics (WMR + Chile + Peru — full draft)

- SCW17-Doc04 — Robustness scenarios and exceptional circumstances (WMR — full draft)

- Slick / trade-off prototype if available (WMR)

- Updated OM status note (WMR)

If any of the above is not in the shared folder by 14:00 CEST Monday 8 June, the chair will downgrade that agenda item from “conclude” to “best-available-state” and flag it as a risk to the Wageningen schedule.

## 2. Email reminder sequence

Three staged reminders. Each is short. Copy/paste blocks below.

### Reminder #1 — Friday 5 June (T-6 days)

Subject: TG-05 (11 June, 15:00 CEST) — read-aheads due Mon 8 Jun 14:00 CEST

Dear all,

A reminder that TG-05 — Pre-Wageningen Final Preparation is Thursday 11 June, 15:00–16:30 CEST (Zoom/Teams). This is the last Task Team call before the Wageningen MSE workshop (15–19 June). The purpose is to close open items, not to reopen them.

The six items on the table:

- Conclude the stock-hypothesis treatment.

- Finalise performance metrics, time horizons, and risk tolerance.

- Freeze MP specifications (data, tuning, HCR, Buffer/K60). No new MPs after TG-05.

- Agree the complete robustness scenario matrix.

- Agree cross-platform validation protocol and assign responsibilities.

- Agree Wageningen communication and decision-making format.

Per the working-papers plan, the following are due Saturday 6 June and should appear in the shared folder no later than 14:00 CEST Monday 8 June so members can read before the call:

- Full draft MSE-01 (Candidate MPs) — WMR + Chile + Peru

- Full draft MSE-02 (Performance metrics and trade-off framework) — Chair

- Full draft MSE-03 (Robustness testing design) — WMR

- Updated OM status note — WMR

- Slick / trade-off prototype if available — WMR

All current SCW17 materials are at https://sprfmo.github.io/scw17/.

If you cannot meet the deadline for the paper you lead, please flag it to me by reply today so we can plan around it.

Best, Jim

### Reminder #2 — Tuesday 9 June (T-2 days)

Subject: TG-05 Thursday 15:00 CEST — agenda + what each member should bring

Dear all,

TG-05 is in two days. Detailed agenda below; please review and bring concrete positions on the items in your area of responsibility.

Agenda (90 minutes, strict time-boxes):

- 15:00–15:05 — Opening

- 15:05–15:20 — Conclude stock-hypothesis treatment

- 15:20–15:35 — Finalise performance metrics, time horizons, risk tolerance

- 15:35–15:55 — Freeze MP specifications (no new MPs after this item)

- 15:55–16:15 — Agree complete robustness scenario matrix

- 16:15–16:25 — Cross-platform validation responsibilities and timeline

- 16:25–16:30 — Wageningen logistics and close

What each member should bring:

- WMR (Iago, Karolina): confirmation that MSE-01, MSE-03, and the updated OM status note are in the shared folder; the proposed MP register (one row per MP with data streams, tuning target, HCR, Buffer/K60); the proposed reference-set vs. robustness-set scenarios; the Slick / trade-off prototype if available.

- Chile (Jose, Aquiles, Ignacio, Sebastian): position on the stock-hypothesis treatment and, if applicable, on whether model-free / OpenMSE MPs from the Chilean contribution should enter the frozen MP register; commitment on Chile’s share of the FLR vs. RTMB/OpenMSE cross-platform validation.

- Peru (Ana, Criscely, Gersson, Erich, Daniel): position on the stock-hypothesis treatment; commitment on Peru’s share of cross-platform validation; any final Peru-specific input to robustness scenarios (e.g., Peru-acoustic uncertainty bands, far-north recruitment regime).

- EU / PFA (Niels): confirmation on performance-metric thresholds and risk tolerance from a Commission-decision perspective; any objections to the Chilean effort-creep treatment carried into the OM that must be tabled before Wageningen rather than at Wageningen.

- Chair (Jim): MSE-02 final draft (metrics, horizons, risk tolerance); proposed Wageningen presentation format and decision-making protocol; the consolidated “exceptional circumstances” meta-rules note (one page).

Ground rules for the call:

- Items 2–4 are CONCLUDE items. If we cannot conclude, we adopt the documented fallback rather than spilling into Wageningen.

- No new MPs, no new metrics, no new OM axes will be added after this call. Items raised after TG-05 go to SC14 documentation, not Wageningen.

All materials at https://sprfmo.github.io/scw17/. Joining link in the calendar invite.

Best, Jim

### Reminder #3 — Thursday 11 June, 08:00 CEST (morning of)

Subject: TG-05 today 15:00 CEST — joining link + last-minute items

Quick reminder: TG-05 today, 15:00 CEST, 90 minutes. Joining link is in the calendar invite (and pasted below for anyone whose invite is missing).

Please be ready at the start of the call with the one decision in your area. The chair will move firmly through the time-boxes — if a topic is not concluded inside its slot, we adopt the documented fallback for that item and move on.

Outstanding items as of this morning:

- (list any papers still missing from the shared folder, with the responsible lead and the fallback the chair will apply)

Joining link: (paste link)

See you at 15:00.

Jim

## 3. Per-recipient focus points (for personalised reminders)

Use these as one-liner additions to direct reminders if you want to nudge specific members.

| Recipient | Single most important thing to bring |
| --- | --- |
| Iago (WMR) | Frozen MP register table; robustness scenario matrix; Slick prototype. |
| Karolina (WMR) | Updated OM status note; confirmation of MSE-01/MSE-03 drafts in shared folder. |
| Niels (PFA/EU) | EU position on performance-metric thresholds and risk tolerance; any reservations on the Chilean creep treatment carried into the OM. |
| Jose Zenteno (IFOP) | Confirmed Chilean position on stock-hypothesis treatment and on the design-based vs. spatio-temporal acoustic index for robustness. |
| Aquiles (INPESCA) | INPESCA’s contribution to the robustness set (acoustic-modelling sensitivity). |
| Ignacio Paya (IFOP) | Confirmed implementation of the effort-creep treatment for cross-check at Wageningen. |
| Ana Alegre (IMARPE) | Peru’s position on stock-hypothesis treatment; commitment on cross-platform validation. |
| Criscely (IMARPE) | Peru length-frequency status and any update to far-north composition input. |
| Gersson (IMARPE) | Final Peru CPUE input for cross-check at Wageningen. |
| Qi Lee (UW, invited) | Independent read on the frozen MP set and on the cross-platform validation protocol. |

## 4. Fallbacks if read-aheads slip

If one or more of MSE-01 / MSE-02 / MSE-03 is not in the shared folder by 14:00 CEST Monday 8 June, the chair will:

- For MSE-01 missing or partial: carry the MP set frozen at TG-04 into Wageningen and add new MPs only as side-by-side comparison runs, not as candidates for SC14 recommendation.

- For MSE-02 missing or partial: adopt the metric list and risk tolerance from the March working-papers plan verbatim; revisit only the time horizons during the call.

- For MSE-03 missing or partial: carry the reference set from TG-04 with the ENSO offshore-drop scenario as the only robustness axis, and flag the missing scenarios as Wageningen-week work.

- For Cross-platform validation: if WMR/Chile/Peru cannot agree owners during the call, the chair appoints owners by name and confirms in the meeting minutes.

These fallbacks are deliberately conservative — the point is to protect Wageningen’s schedule, not to penalise the leads.